TGC RADIOLOGY QUEUEING SYSTEM

Implementation Plan: Prototype to Laragon + MySQL Deployment

Current state: The prototype uses PHP, HTML, CSS, JavaScript, browser localStorage, and IndexedDB. Laragon deployment, MySQL persistence, authentication, server-side queue rules, and audit logging are the remaining implementation work.

# 1. Target Outcome

Deliver a locally deployed radiology queueing system on the hospital LAN using Laragon, PHP, and MySQL. Reception and radiology staff will use authenticated screens, while patients will use a read-only public display. The application will enforce IPD-first queue selection, retain all operational activity, and support permitted reporting and exports.

# 2. Implementation Sequence

Complete the phases in order. Do not connect the existing browser-storage prototype to production use; replace each browser-only data path with a server-side equivalent before live deployment.

| Phase | Main deliverable | Work to complete | Ready when |
| --- | --- | --- | --- |
| 0. Baseline and environment | Working Laragon development environment | Install/configure Laragon; set the project web root to public; create environment variables; preserve a backup of the current prototype; confirm PHP and MySQL versions. | The public landing page, receptionist page, and public-display page load through Laragon on localhost. |
| 1. MySQL schema | Persistent database and initial data | Create migrations for users, procedures, patient categories, counters, tickets, events, advertisements, and audit logs. Seed X-Ray, Ultrasound, CT Scan, IPD, and OPD; set IPD priority above OPD. | All tables use InnoDB, utf8mb4, foreign keys, indexes, and test seed data. |
| 2. Application foundation | Database connection and layered PHP code | Create bootstrap, PDO/MySQL connection, repositories, services, controllers, routes, validation, error logging, and configuration loading. Keep credentials in environment variables. | A test route can read seed data using repository and service layers, without direct SQL in views. |
| 3. Ticket and queue workflow | Server-side ticket lifecycle | Implement atomic ticket creation, daily counters, queue events, call-next, completion, skip, and cancellation. Enforce IPD before OPD within a procedure and FIFO within each category. | Concurrent ticket creation cannot duplicate a code, and every status change produces a queue event. |
| 4. Authentication and roles | Restricted staff access | Create staff accounts, password hashing, login/logout, session protection, and role checks. Limit receptionist, radiology, administrator, and public-display actions by role. | Unauthorized users cannot open staff routes or export data; public display reveals only permitted queue fields. |
| 5. Screen integration | Views connected to server data | Replace localStorage/IndexedDB queue reads and writes with PHP endpoints. Connect reception, queue management, analytics, and public display to the same MySQL records. | A ticket created at reception appears on the queue-management and public-display screens from shared server data. |
| 6. Reports and advertisements | Operational reporting and media workflow | Build filtered report queries and export; move advertisement files to controlled local storage; store metadata and display order in MySQL; validate file types and sizes. | Authorized users can export permitted data and manage approved ads without browser-only storage. |
| 7. Quality and deployment | Tested local release | Run unit/integration tests, workflow tests, role/privacy checks, backup/restore tests, and user acceptance testing. Configure LAN access, backups, logging, and operational handover. | The hospital can restore the database, follow the fallback process, and operate the system from authorized local devices. |

# 3. First Work Session Checklist

Install Laragon and configure the project so its public directory is the web root.

Create a local MySQL database named tgc_radiology_queue and verify a PHP PDO connection using environment variables.

Create the first migration for procedures and patient_categories, then seed X-Ray, Ultrasound, CT Scan, IPD, and OPD with IPD as the higher priority rank.

Create ticket, queue-event, and daily-counter migrations before changing the receptionist screen.

Implement TicketRepository and QueueService, then write a small test script for ticket creation and IPD-first selection.

Only after the server-side workflow passes, replace the localStorage ticket logic in the receptionist view.

# 4. Required Server-Side Rules

Ticket codes are unique per procedure and calendar date. Generate the sequence number inside a MySQL transaction using the daily counter table.

For one procedure, select Waiting IPD tickets before Waiting OPD tickets. For tickets of the same category, select the earliest issue time first.

Only valid state transitions are permitted: Waiting to Serving, Serving to Completed, and authorized Waiting/Serving transitions to Skipped or Cancelled.

Every creation, call, completion, skip, cancellation, view-sensitive export, and advertisement change writes an audit or queue-event record with time and actor.

The public display endpoint returns no patient names, medical record numbers, diagnoses, or clinical results.

# 5. Folder Ownership

| Folder | Purpose | Next implementation work |
| --- | --- | --- |
| app/Controllers | HTTP request handlers | Add TicketController, QueueController, ReportController, AuthController, and AdvertisementController. |
| app/Services | Business rules | Add QueueService, TicketService, ReportService, AdvertisementService, and AuditService. |
| app/Repositories | MySQL data access | Add PDO-backed repositories for each planned table; keep SQL out of views. |
| app/Middleware | Access protection | Add authentication and role middleware before enabling staff routes. |
| database/migrations | Versioned schema | Create and apply the MySQL migrations in the sequence listed above. |
| resources/views | HTML/PHP presentation | Replace prototype browser-storage logic with calls to application endpoints. |
| storage/uploads/ads | Controlled ad files | Use this for validated image/video uploads; store only metadata/path in MySQL. |

# 6. Release Acceptance Checklist

All ticket and queue data is stored in MySQL; no production queue data relies on localStorage or IndexedDB.

IPD priority and FIFO handling are verified with test data for every procedure.

Reception, radiology, administrator, and public-display permissions are tested.

The public display has no patient-identifying or clinical information.

Reports and exports use server-filtered, role-authorized data.

MySQL backup and restore have been tested, and the local host/network fallback process is documented.

Staff have completed user acceptance testing using realistic radiology workflows.